KRACHI EAST MUNICIPAL ASSEMBLY

APPROVED ANNUAL ACTION PLAN FOR 2025

| No. | Programme (PBB) | Sub-Programme (PBB) | Broad Activities | Location | Timeframe |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Dept. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 1 | 2 | 3 | 4 | GoG | IGF | Others | New | Ongoing | Lead | Collabo |
| 1 | Economic Dev’t | Trade, Indus. and Tourism Serv | Training and Re-activation of VSLA groups | All 5 Clusters | x | x | x | x |  |  | 500,000.00 (SOCO) | x |  | GEA | Central Adm. |
| 2 | Economic Dev’t | Trade, Indus. and Tourism Serv | Provision of Financial Support to Groups | All 5 Clusters | x | x | x | x |  |  | 1,000,000.00 (SOCO) | x |  | GEA | Central Adm. |
| 3 | Economic Dev’t | Trade, Indus. and Tourism Serv | Re-development of Phase 1 Dambai Market to include: a 1No. 2-Storey (with 32No. Lockable stores, 8No. Washrooms) | Dambai | x | x | x | x |  |  | 1,780,811.80 (GSCSP) |  | x | MWD | Central Adm. |
| 4 | Economic Dev’t | Trade, Indus. and Tourism Serv | Construction of a 24-Hour Economy Model Market | Dambai |  |  | x | x | 4,961,091.86 |  |  | x |  | MWD | Central Adm. |
| 5 | Economic Dev’t | Trade, Indus. and Tourism Serv | Construction of a Fence wall around Dambai Market | Dambai Market |  |  | x | x |  |  | 800,000.00 (SOCO) | x |  | MWD | Central Adm. |
| 6 | Economic Dev’t | Trade, Indus. and Tourism Serv | Construction of 3No. 10bay Open Sheds | Dambai Market |  |  | x | x |  |  | 550,000.00 (SOCO) | x |  | MWD | Central Adm. |
| 7 | Economic Dev’t | Trade, Indus. and Tourism Serv | Prepare a Financial Resources Plan | Dambai | x | x | x | x |  |  | 100,000.00 (GSCSP) | x |  | MPCU | Central Adm. |
| 8 | Economic Dev’t | Trade, Indus. and Tourism Serv | Organize business and community to participate in fee fixing consultations | Dambai | x | x | x | x | 60,000.00 |  |  |  | x | Budget Unit | Central Adm. |
| 9 | Economic Dev’t | Trade, Indus. and Tourism Serv | Monitoring of implementation of LED activities | Dambai | x | x | x | x | 30,000.00 | 10,000.00 |  |  | x | GEA | Central Adm. |
| 10 | Economic Dev’t | Trade, Indus. and Tourism Serv | Support cultural activities to promote domestic tourism | Municipal-wide | x | x | x | x | 15,000.00 | 10,000.00 |  | x |  | Central Adm. | CNC |
| 11 | Economic Dev’t | Trade, Indus. and Tourism Serv | Re-development of Phase 2 Dambai Market to include: a Paving of 4,500square metres floor approx. in front of the Main Market | Dambai | x | x | x | x |  |  | 4,104,540.00 (GSCSP) | x |  | MWD | Central Adm. |
| 12 | Economic Dev’t | Trade, Indus. and Tourism Serv | Re-development of Phase 3 Dambai Market to include: bituminous surfacing of 0.60km inner market roads with 1.40km covered U-drains | Dambai | x | x | x | x |  |  | 4,104,540.00 (GSCSP) | x |  | MWD | Central Adm. |
| 13 | Economic Dev’t | Trade, Indus. and Tourism Serv | Construction of 1No. Double Cell 2m * 2m Box Culvert to connect Market Centre | Tokuroano |  |  | x | x |  |  | 1,325,000.00 (SOCO) | x |  | MWD | Central Adm. |
| 14 | Economic Dev’t | Agricultural Serv and Mgt | Train 500 farmers on good agronomic practices (GAPs) and adoption of improved crops and livestock production technologies | Municipal-wide | x | x | x | x |  |  | 5000.00 |  | x | Agric Dept. | Central Adm. |
| 15 | Economic Dev’t | Agricultural Serv and Mgt | Identify and train 20 processors, and marketers on standardization, packaging and branding | Municipal-wide | x | x | x | x |  |  | 4000.00 |  | x | Agric Dept. | Central Adm. |
| 16 | Economic Dev’t | Agricultural Serv and Mgt | Build capacity of 20 cassava processors on processing of cassava into different products | Municipal-wide | x | x | x | x | 1500.00 |  | 1500.00 | x |  | Agric Dept. | Central Adm. |
| 17 | Economic Dev’t | Agricultural Serv and Mgt | Train 10 extension and 5 veterinary technical staff and 40 livestock farmers in the prevention of scheduled livestock and rural poultry diseases | Municipal-wide | x | x | x | x | 1500.00 |  | 3000.00 |  | x | Agric Dept. | Central Adm. |
| 18 | Economic Dev’t | Agricultural Serv and Mgt | Educate pet owners on the importance of vaccination against Zoonotic diseases in animals | Municipal-wide | x | x | x | x | 2500.00 |  | 2500.00 |  | x | Agric Dept. | Central Adm. |
| 19 | Economic Dev’t | Agricultural Serv and Mgt | Internal mgt | Municipal-wide | x | x | x | x |  |  | 6000.00 |  | x | Agric Dept. | Central Adm. |
| 20 | Economic Dev’t | Agricultural Serv and Mgt | Monitoring and extension services | Municipal-wide | x | x | x | x |  |  | 16,000.00 |  | x | Agric Dept. | Central Adm. |
| 21 | Economic Dev’t | Agricultural Serv and Mgt | Organize Farmers’ Day | Municipal-wide | x | x | x | x | 68,000.00 |  |  |  | x | Agric Dept. | Central Adm. |
| 1 | Social Serv. Delivery | Public Health Serv and Mgt | Support expanded programme of immunization (EPI) | Municipal-wide |  | x |  | x | 10,000.00 | 10,000.00 |  |  | x | MHD | Central Adm. |
| 2 | Social Serv. Delivery | Public Health Serv and Mgt | Support malaria Elimination programme | Municipal-wide | x | x | x | x | 30,000.00 |  |  |  | x | MHD | Central Adm. |
| 3 | Social Serv. Delivery | Public Health Serv and Mgt | Procure equipment for health service delivery | Municipal-wide | x | x | x | x | 40,000.00 |  |  |  | x | MHD | Central Adm. |
| 4 | Social Serv. Delivery | Public Health Serv and Mgt | Support HIV/AIDS programmes | Municipal-wide | x | x | x | x | 20,000.00 | 10,000.00 |  |  | x | Central Adm. | MHD |
| 5 | Social Serv. Delivery | Public Health Serv and Mgt | Embark on Disease surveillance activities | Municipal-wide | x | x | x | x | 50,000.00 | 10,000.00 |  |  | x | MHD | Central Adm. |
| 6 | Social Serv. Delivery | Public Health Serv and Mgt | Re-Roofing of 1No. OPD Section at Health Centre | Dambai Health Centre |  | x |  |  | 160,000.00 |  |  | x |  | MWD | MHD/Central Adm. |
| 7 | Social Serv. Delivery | Public Health Serv and Mgt | Support the Typhoid Control Programme | Municipal Wide |  |  | x | x | 8,000.00 |  |  |  | x | MWD | MHD/Central Adm. |
| 8 | Social Serv. Delivery | Public Health Serv and Mgt | Support Integrated Island Outreach Services | Municipal Wide |  |  | x | x | 25,000.00 |  |  |  | x | MWD | MHD/Central Adm. |
| 9 | Social Serv. Delivery | Public Health Serv and Mgt | Support Community Score Cards for the Community Health Committee by CSO quarterly | Municipal Wide |  |  | x | x | 6,000.00 |  |  |  | x | MWD | MHD/Central Adm. |
| 10 | Social Serv. Delivery | Public Health Serv and Mgt | Support Infant and young child feeding | Municipal Wide |  |  | x | x | 7,500.00 |  |  |  | x | MWD | MHD/Central Adm. |
| 11 | Social Serv. Delivery | Public Health Serv and Mgt | Renovation of Nurses Quarters | Adumadum |  |  | x | x | 350,000.00 |  |  | x |  | MWD | MHD/Central Adm. |
| 12 | Social Serv. Delivery | Public Health Serv and Mgt | Construction and furnishing of 2No. CHPS Compounds with extension of Electricity and Mechanized Water Systems | Monkrate, Nanso |  |  | x | x | 1,984,436.74 |  |  | x |  | MWD | MHD/Central Adm. |
| 13 | Social Serv. Delivery | Public Health Serv and Mgt | Partially complete the CODA Health facility | Dambai Health Centre |  |  |  |  | 680,000.00 |  |  |  | x | MWD | MHD/Central Adm. |
| 14 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Construction and Completion of 1No. 3-Unit Classroom Block with landscaping | DACE | x | x | x | x | 142,092.00 |  |  |  | x | MWD | MED/Central Adm. |
| 15 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Construction and Completion of 1No. 3-Unit Classroom Block with landscaping | Ayeremu | x | x | x | x | 47,007.66 |  |  |  | x | MWD | MED/Central Adm. |
| 16 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Construction and Completion of 1No. 6-Unit Classroom Block with landscaping | Pai-Katanga | x | x | x | x | 366,694.20 |  |  |  | x | MWD | MED/Central Adm. |
| 17 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Renovation of 1No. 6-Unit Classroom Block | Pai-Katanga | x | x | x | x | 17,792.57 |  |  |  | x | MWD | MED/Central Adm. |
| 18 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Organise “My First Day” at School Programme | Municipal-wide | x |  | x |  | 15,000.00 | 5,000.00 |  |  | x | MED | Central Adm. |
| 19 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Organise “National Independence Day Celebration | Municipal-wide | x |  |  |  | 60,000.00 | 5,000.00 |  |  | x | MED | Central Adm. |
| 20 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Sponsor Science, Mathematics and Technology, Innovation (STMIE) clinic | Municipal-wide |  |  | x |  | 10,000.00 | 10,000.00 |  |  | x | MED | Central Adm. |
| 21 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Support BECE mock Exams | Municipal-wide |  | x |  |  | 10,000.00 | 5,000.00 |  |  | x | MED | Central Adm. |
| 22 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Construct and Furnish 1No. 3-Unit JHS Classroom Block with a store, office, 2No. Girls Changing Room, office, 2-Unit Urinal and 1No. 4-Unit KVIP & Supply of 120 Mono Desks | Girls Model School Dambai | x | x | x | x |  |  | 1,500,000.00 (SOCO) | x |  | MED | MWD/Central Adm. |
| 23 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Construct and Furnish 1No. 3-Unit JHS Classroom Block with a store, office, 2No. Girls Changing Room, office, 2-Unit Urinal and 1No. 4-Unit KVIP & Supply of 120 Mono Desks | Nanum Cement M/A Primary | x | x | x | x |  |  | 1,500,000.00 (SOCO) | x |  | MED | MWD/Central Adm. |
| 24 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Construction of Astro Turf for Youth Development Activities | Lapaz Park, Dambai | x | x | x | x |  |  | 3,200,000.00 (SOCO) | x |  | MED | MWD/Central Adm. |
| 25 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Organize Cluster level Inter Community sports for development events | Njare, Dambai, Ayeremu, Adumadum & Tokuroano | x | x | x | x |  |  | 200,000.00 (SOCO) | x |  | MED | MWD/Central Adm. |
| 26 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Support the Construction of 3No. Youth Parliament Centres | Tokuroano, Ayeremu, Adumadum | x | x | x | x |  |  | 216,000.00 (SOCO) | x |  | MED | MWD/Central Adm. |
| 27 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Construct and Furnish 1No. 2-Unit KG Classroom Block with a store, office, 2-Unit Urinal and 1No. 4-Unit KVIP & Supply of 12No. Hexagonal Tables, 72No. Chairs & 3No. Teachers Table and Chair | Bawa Akura | x | x | x | x |  |  | 450,000.00 (DACF/RFG) | x |  | MED | MWD/Central Adm. |
| 28 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Support to Needy but brilliant students | Municipal Wide |  |  | x | x | 85,000.00 |  |  | x |  | MED | Central Adm. |
| 29 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Provide dual desks for basic schools, hexagonal desks for KGs, mono desks for JHS/SHS and teachers table and chairs | Municipal-wide |  | x | x |  | 1,984,436.74 |  |  | x |  | MED | MWD/Central Adm. |
| 30 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Construct and Furnish 1No. 3-Unit JHS Classroom Block with a store, office, 2No. Girls Changing Room, office, 2-Unit Urinal and 1No. 4-Unit KVIP & Supply of 120 Mono Desks | Kudorkope M/A Primary | x | x | x | x |  |  | 1,200,000.00 (SOCO) | x |  | MED | MWD/Central Adm. |
| 31 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Construct and Furnish 1No. 3-Unit JHS Classroom Block with a store, office, 2No. Girls Changing Room, office, 2-Unit Urinal and 1No. 4-Unit KVIP & Supply of 120 Mono Desks | Dormabin English & Arabic School | x | x | x | x |  |  | 1,200,000.00 (SOCO) | x |  | MED | MWD/Central Adm. |
| 32 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Construct and Furnish 1No. 3-Unit 60-Double Bed Capacity Dormitory for Girls Model School | Girls Model School Dambai | x | x | x | x |  |  | 1,500,000.00 (SOCO) | x |  | MED | MWD/Central Adm. |
| 33 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Construction of Ultra-Modern Volleyball Court for Youth Development Activities | Lapaz Park, Dambai |  |  | x | x |  |  | 216,000.00 (SOCO) | x |  | MED | MWD/Central Adm. |
| 34 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Construct and Furnish 1No. 2-Unit KG Classroom Block with a store, office, 2-Unit Urinal and 1No. 4-Unit KVIP | Okuma Akura |  |  | x | x | 500,000.00 |  |  |  | x | MED | MWD/Central Adm. |
| 35 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Construct and Furnish 1No. 6-Unit JHS Classroom Block with office, 1 No. Girls Changing Room, 2-Unit Urinal | Yariga No. 2 |  |  | x | x | 820,000.00 |  |  |  | x | MED | MWD/Central Adm. |
| 36 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Construct and Furnish 1No. 3-Unit Classroom Block with office, 1 No. Girls Changing Room, 2-Unit Urinal | Kpelema Hope for Life |  |  | x | x | 550,000.00 |  |  |  | x | MED | MWD/Central Adm. |
| 37 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Rehabilitate Teachers' quarters and clad pavilion block | Kpachiri |  |  |  |  | 400,000.00 |  |  |  | x | MED | MWD/Central Adm. |
| 38 | Social Serv. Delivery | Educ., Youth & Sports and Libr. Services | Rehabilitate and clad 1No. 6-Unit Pavilion block | Kelentin |  |  |  |  | 400,000.00 |  |  |  | x | MED | MWD/Central Adm. |
| 39 | Social Serv. Delivery | Social Welfare and Comm. Serv | Promote juvenile justice and administration | Municipal-wide | x | x | x | x | 8,000.00 | 7,000.00 |  |  | x | SW&CD | Central Adm. |
| 40 | Social Serv. Delivery | Social Welfare and Comm. Serv | Promote Child and Family Welfare | Municipal-wide | x | x | x | x | 10,000.00 |  |  |  | x | SW&CD | Central Adm. |
| 41 | Social Serv. Delivery | Social Welfare and Comm. Serv | Undertake child protection activities | Municipal-wide | x | x | x | x | 15,000.00 |  |  |  | x | SW&CD | Central Adm. |
| 42 | Social Serv. Delivery | Social Welfare and Comm. Serv | Register, inspect and monitor Early Childhood Dev’t. Centres and NGOs | Municipal-wide | x | x | x | x | 20,000.00 |  |  |  | x | SW&CD | Central Adm. |
| 43 | Social Serv. Delivery | Social Welfare and Comm. Serv | Establish PWDs in income generation activities (health,education) | Municipal-wide | x | x | x | x | 100,000.00 |  |  |  | x | SW&CD | Central Adm. |
| 44 | Social Serv. Delivery | Social Welfare and Comm. Serv | Financial assistance to PWDs | Municipal-wide | x | x | x | x | 50,000.00 |  |  |  | x | SW&CD | Central Adm. |
| 45 | Social Serv. Delivery | Social Welfare and Comm. Serv | Support case management | Municipal-wide | x | x | x | x | 10,000.00 | 10,000.00 |  |  | x | SW&CD | Central Adm. |
| 46 | Social Serv. Delivery | Social Welfare and Comm. Serv | Monitoring and Supervision of School Feeding Programme | Municipal-wide | x | x | x | x | 10,000.00 |  |  |  | x | MED | Central Adm. |
| 47 | Social Serv. Delivery | Social Welfare and Comm. Serv | Renew and enroll LEAP beneficiaries on NHIS platform | Municipal-wide | x | x | x | x | 5,000.00 |  |  |  | x | SW&CD | Central Adm. |
| 48 | Social Serv. Delivery | Social Welfare and Comm. Serv | Support the combat of domestic violence against women and child trafficking | Municipal-wide | x | x | x | x |  |  | 20,000.00 (UNICEF) |  | x | SW&CD | Central Adm. |
| 49 | Social Serv. Delivery | Social Welfare and Comm. Serv | Community sensitization to prevent violence against Girls/Women | Selected communities | x | x | x | x |  |  | 15,000.00 (UNICEF) |  | x | SW&CD | Central Adm. |
| 50 | Social Serv. Delivery | Social Welfare and Comm. Serv | Community engagement on how to manage properties acquired in marriage | Selected communities | x | x | x | x |  |  | 10,000.00 (UNICEF) |  | x | SW&CD | Central Adm. |
| 51 | Social Serv. Delivery | Social Welfare and Comm. Serv | Prepare a comprehensive strategic Gender Mainstreaming Plan | Dambai | x | x | x | x |  |  | 90,000.00 (GSCSP) |  |  |  |  |
| 52 | Social Serv. Delivery | Social Welfare and Comm. Serv | Registration of Births and Deaths | Municipal-wide | x | x | x | x | 10,000.00 |  |  |  | x | Birth & Death Registry | Central Adm. |
| 1 | Env. Mgt | Env. Health & San. Serv | Screening and Sensitization of Food Vendors and School Feeding Caterers | Municipal-wide | x | x | x | x | 30,000.00 |  |  |  | x | EHU/GHS | Central Adm. |
| 2 | Env. Mgt | Env. Health & San. Serv | Support the promotion of Community Led Total Sanitation | Municipal-wide | x | x | x | x | 50,000.00 | 20,000.00 |  |  | x | Env. Health Unit | Central Adm. |
| 3 | Env. Mgt | Env. Health & San. Serv | Organize Environmental Health Promotion Activities and Clean Up Exercises | Municipal-wide | x | x | x | x | 40,000.00 | 15,000.00 |  |  | x | Env. Health Unit | Central Adm. |
| 4 | Env. Mgt | Env. Health & San. Serv | Management of Sanitation (SIP, Fumigation, liquid waste management, Waste Landfill Management) | Municipal-wide | x | x | x | x | 500,000.00 |  |  |  | x | Env. Health Unit | Central Adm. |
| 5 | Env. Mgt | Env. Health & San. Serv | Procure Sanitary Tools | Municipal-wide | x | x | x | x | 50,000.00 |  |  |  | x | Env. Health Unit | Central Adm. |
| 6 | Env. Mgt | Env. Health & San. Serv | Enforcement of Environmental Sanitation Bye-laws and Regulations | Municipal-wide | x | x | x | x | 30,000.00 |  |  |  | x | Env. Health Unit | Central Adm. |
| 7 | Env. Mgt | Env. Health & San. Serv | Construct 1No. Slaughter Slab | Katanga | x | x | x | x | 150,000.00 |  |  | x |  | MWD | Central Adm. |
| 8 | Env. Mgt | Env. Health & San. Serv | Dislodgement of toilets | Municipal-wide | x | x | x | x | 150,000.00 |  |  | x |  | MWD | Central Adm. |
| 9 | Env. Mgt | Env. Health & San. Serv | Construction of Household Toilets | Dambai Old Town & Dambai Junction | x | x | x | x |  |  | 553,051.23 (GPSNP II) | x |  | Env. Health Unit | Central Adm. |
| 10 | Env. Mgt | Disaster Prev. & Mgt | Organize disaster preventive & mitigation programmes | Municipal-wide | x | x | x | x | 10,000.00 |  |  |  | x | NADMO | GNFS/Central Adm. |
| 11 | Env. Mgt | Disaster Prev. & Mgt | Procure relief items for disaster victims | Municipal-wide | x | x | x |  | 40,000.0 | 20,000.00 |  |  | x | NADMO | Central Adm. |
| 12 | Env. Mgt | Disaster Prev. & Mgt | Supply of seedlings | Municipal-wide | x | x | x | x | 20,000.00 | 20,000.00 |  |  | x | NADMO | Central Adm./Forestry |
| 13 | Env. Mgt | Disaster Prev. & Mgt | Rehabilitation of degraded land using Cashew Trees/Mango Trees | Tapon | x | x | x | x |  |  | 659,153.70 (GPSNP 2) | x |  | NADMO | Central Adm./Forestry |
| 14 | Env. Mgt | Disaster Prev. & Mgt | Training of NADMO staff and Fire Volunteers on Disaster Management | Dambai | x | x | x | x |  |  | 60,000.00 (GSCSP) | x |  | MPCU | Central Adm. |
| 15 | Env. Mgt | Disaster Prev. & Mgt | Undertake Environmental and social safeguard activities | Dambai Market | x | x | x | x |  |  | 250,000.00 (GSCSP) | x |  | MPCU | Central Adm. |
| 16 | Env. Mgt | Env. Health & San. Serv | Procure 10No. 12m2 skip container | Municipal-wide | x | x | x | x | 220,000.00 |  |  | x |  | Env. Health Unit | Central Adm. |
| 17 | Env. Mgt | Env. Health & San. Serv | Construction of 1No. 20-Seater WC toilet | Dambai Market | x | x | x | x | 450,000.00 |  |  | x |  | Env. Health Unit | Central Adm. |
| 18 | Env. Mgt | Env. Health & San. Serv | Evacuation of Solid waste | Municipal-wide |  |  | x | x | 45,000.00 |  |  | x |  | Env. Health Unit | Central Adm. |
| 1 | Infra. Deliv. and Mgt | Public Works, Rur, Housing & Water Mgt | Siting, Drilling and Mechanization of 10No. Boreholes | Okuma Akura, Katanga, Israel, Abongo, Pompi, Chamba Akura, Ankra Akura, Dambai H/C, M/A, Lapaz Park, Adorkope |  |  |  |  | 1,984,436.74 |  |  | x |  | MWD | Central Adm. |
| 2 | Infra. Deliv. and Mgt | Spatial Planning | Pillar all Assembly properties | Municipal-wide | x | x | x | x | 10,000.00 | 10,000.00 |  | x |  | MPPD | Central Adm. |
| 3 | Infra. Deliv. and Mgt | Spatial Planning | Prepare local plans | Dambai & Pai-Katanga | x | x | x | x | 30,000.00 | 10,000.00 |  | x |  | MPPD | Central Adm. |
| 4 | Infra. Deliv. and Mgt | Spatial Planning | Expand the Street Addressing & Prop Numbering Project | Municipal-wide | x | x | x | x | 30,000.00 | 20,000.00 | 70,000.00 (GSCSP) |  | x | MPPD | Central Adm. |
| 5 | Infra. Deliv. and Mgt | Spatial Planning | Supervision and Regulation of Infrastructural Development | Municipal-wide | x | x | x | x | 40,000.00 |  |  |  | x | MPPD | Central Adm. |
| 6 | Infra. Deliv. and Mgt | Spatial Planning | Acquisition and Documentation of all Government Lands | Municipal-wide | x | x | x | x | 50,000.00 | 30,000.00 |  |  | x | MPPD | Central Adm. |
| 7 | Infra. Deliv. and Mgt | Spatial Planning | Organize Tech Sub-Com and Spatial Planning Meetings | Dambai | x | x | x | x | 27,000.00 | 25,000.00 |  |  | x | MPPD | Central Adm. |
| 8 | Infra. Deliv. and Mgt | Urban Roads & Transport Serv. | Rehabilitation of Feeder Roads | Tsafo Jnx. – Tsafoakura Wankayaw-Ankrah Akura | x | x | x | x |  |  | 2,250,000.00 (GPSNP 2) | x |  | MWD | MPPD/Central Adm. |
| 9 | Infra. Deliv. and Mgt | Urban Roads & Transport Serv. | Update Municipal Roads, Pedestrian walkway and Drainage Master Plans | Dambai | x | x | x | x |  |  | 90,000.00 (GSCSP) | x |  | MPCU | MPPD/Central Adm. |
| 10 | Infra. Deliv. and Mgt | Urban Roads & Transport Serv. | Sensitization of road users on road signs | Dambai | x | x | x | x | 20,000.00 |  |  | x |  | MWD | MPPD/Central Adm. |
| 11 | Infra. Deliv. and Mgt | Urban Roads & Transport Serv. | Construction of speed ramps along major roads | Asukawkaw | x | x | x | x | 50,000.00 |  |  | x |  | MWD | MPPD/Central Adm. |
| 12 | Infra. Deliv. and Mgt | Urban Roads & Transport Serv. | Desilting of Drains | Dambai | x | x | x | x | 10,000.00 |  |  | x |  | MWD | MPPD/Central Adm. |
| 13 | Infra. Deliv. and Mgt | Urban Roads & Transport Serv. | Weeding/Grass cutting along roads | Dambai | x | x | x | x | 20,000.00 |  |  | x |  | MWD | MPPD/Central Adm. |
| 14 | Infra. Deliv. and Mgt | Urban Roads & Transport Serv. | Sweeping along roads | Dambai | x | x | x | x | 8,000.00 |  |  | x |  | MWD | MPPD/Central Adm. |
| 15 | Infra. Deliv. and Mgt | Public Works, Rur, Housing & Water Mgt | Installation and maintenance of street lights | Municipal-wide | x | x | x | x | 60,000.00 | 30,000.00 |  |  | x | MWD | Central Adm. |
| 16 | Infra. Deliv. and Mgt | Public Works, Rur, Housing & Water Mgt | Construction of Small Earth Dams | Kparekpare | x | x | x | x |  |  | 800,000.00 (GPSNP 2) | x |  | MWD | MPPD/Central Adm. |
| 17 | Infra. Deliv. and Mgt | Public Works, Rur, Housing & Water Mgt | Support Community Initiated Projects sustainably | Municipal-wide | x | x | x | x | 100,000.00 |  |  | x |  | MWD | Central Adm. |
| 18 | Infra. Deliv. and Mgt | Public Works, Rur, Housing & Water Mgt | Filling, Grassing and Fencing of Public Parks/Spaces | Municipal-wide | x | x | x | x |  |  | 800,000.00 (GPSNP 2) | x |  | MWD | Central Adm. |
| 19 | Infra. Deliv. and Mgt | Public Works, Rur, Housing & Water Mgt | Siting, Drilling and Mechanization of Boreholes | Dambai | x | x | x | x |  |  | 800,000.00 (GPSNP 2) | x |  | MWD | Central Adm. |
| 1 | Mgt & Admin. | General Admin. | Implement operation and maintenance plan | Municipal-wide | x | x | x | x | 300,000.00 | 60,000.00 |  |  | x | MWD | Central Adm. |
| 2 | Mgt & Admin. | General Admin. | Construction and Completion of 1No. 2-Bedroom Bungalow for MCD | Dambai | x | x | x | x | 14,533.57 |  |  |  | x | MWD | Central Adm. |
| 3 | Mgt & Admin. | General Admin. | Organise all mandatory & stat. meetings of the Assembly | Municipal-wide | x | x | x | x | 100,000.00 | 60,000.00 |  |  | x | Central Adm. | Other Depts. |
| 4 | Mgt & Admin. | General Admin. | Organise 12No. Zonal Council Meetings | Municipal-wide | x | x | x | x | 10,000 | 30,000.00 |  |  | x | Central Admin | Other Depts. |
| 5 | Mgt & Admin. | General Admin. | Implement Municipal Anti-Corruption Plan | Municipal wide | x | x | x | x |  | 15,000.00 |  |  | x | NCCE | Central Adm. |
| 6 | Mgt & Admin. | General Admin. | Undertake auditing activities | Municipal wide | x | x | x | x | 40,000.00 |  |  |  | x | I.A. | Central Adm. |
| 7 | Mgt & Admin. | General Admin. | Conduct Civic Education Programmes | Municipal wide | x | x | x | x | 15,000.00 | 5,000.00 |  | x |  | NCCE | Central Adm. |
| 8 | Mgt & Admin. | General Admin. | Procure set of office furniture | Offices of KEMA | x | x | x | x | 100,000.00 |  |  | x |  | Central Adm. | MWD |
| 9 | Mgt & Admin. | General Admin. | Procure Desktops and laptops | Offices of KEMA | x | x | x | x | 50,000.00 |  |  | x |  | Central Adm, | Other Depts. |
| 10 | Mgt & Admin. | General Admin. | Procure stationery and printing materials | Offices of KEMA | x | x | x | x | 100,000.00 | 60,000.00 |  | x |  | Central Adm, |  |
| 11 | Mgt & Admin. | General Admin. | Support statistical Dept. | Dambai | x | x | x | x | 15,000.00 |  |  |  | x | Central Adm. | Stats. Dept. |
| 12 | Mgt & Admin. | General Admin. | Support internal management of the organization. | KEMA | x | x | x | x | 200,000.00 |  |  |  | x | Central Adm. |  |
| 13 | Mgt & Admin. | General Admin. | Mobilise communities, Constitute and Engage CPICs | Beneficiary Communities | x | x | x | x |  |  | 100,000.00 (SOCO) |  | x | ISD | Central Adm. |
| 14 | Mgt & Admin. | General Admin. | Disseminate govt policies and progs to community members | Municipal-wide | x | x | x | x | 5,000.00 | 6,000.00 |  |  | x | ISD | Central Adm. |
| 15 | Mgt & Admin. | General Admin. | Implement MP’s programmes and projects | Municipal-wide | x | x | x | x | 500,000.00 |  |  |  | x | MP | Central Adm. |
| 16 | Mgt & Admin. | Planning, Budgeting, M&E | Preparation of 2026-2029 MTDP, Budget and Fee-Fixing Resolution | Municipal-wide |  | x | x |  | 640,000.00 |  |  |  | x | Central Adm. | Other Depts. |
| 17 | Mgt & Admin. | Planning, Budgeting, M&E | Organize at least 2 PFM Town Hall Meetings | Municipal-wide | x |  | x |  | 80,000.00 |  |  |  | x | Central Adm. | Other Depts. |
| 18 | Mgt & Admin. | Planning, Budgeting, M&E | Organize MPCU, inspect, Monitor and Evaluate Prog and Projects | Municipal-wide | x | x | x | x | 60,000.00 |  | 400,000.00 (SOCO) 200,000.00 (GSCSP) |  | x | Central Adm. | Other Depts. |
| 19 | Mgt & Admin. | Human Resource | Undertake capacity building programmes and provision of logistics | Dambai | x | x | x | x | 60,000.00 | 20,000.00 |  |  | x | HRD | Central Adm. |
| 20 | Mgt & Admin. | Security | Renovation of Magistrates Residency | Dambai | x | x | x | x | 105,950.00 |  |  |  | x | MWD | Central Adm. |
| 21 | Mgt & Admin. | Security | Rehabilitation and Furnishing of Magistrate Court Premises | Dambai | x | x | x | x |  |  | 536,393.00 (SOCO) |  | x | MWD | Central Adm. |
| 22 | Mgt & Admin. | Security | Support organization of MUSEC meetings and activities | Dambai | x | x | x | x | 80,000.00 |  |  |  | x | Central Adm. | Security Services |
| 23 | Mgt & Admin. | General Admin. | Rehabilitation of KEMA office (for GES) and Staff Bungalows | Dambai |  |  | x | x | 679,811.35 |  |  |  | x | MWD | Central Adm. |
| 24 | Mgt & Admin. | General Admin. | Rehabilitation of Substructures | Nkabom & Asukawkaw |  |  | x | x | 150,000.00 |  |  |  | x | MWD | Central Adm. |
| 25 | Mgt & Admin. | General Admin. | Payment of allowances to Hon. Assembly Members | Municipal Wide |  |  | x | x | 351,000.00 |  |  |  | x | MWD | Central Adm. |

## SUMMARY OF 2025 APPROVED ACTION PLAN

| S/N | Programme | No. of Activities | Total Budget (GHS) |
| --- | --- | --- | --- |
|  | Economic Development | 21 | 19,462,483.66 |
|  | Social Services Delivery | 52 | 20,405,959.91 |
|  | Environmental Management | 18 | 3,382,204.93 |
|  | Infrastructure Delivery and Management | 19 | 7,374,436.74 |
|  | Management and Administration | 25 | 5,148,687.92 |
| Total |  | 135 | 55,773,773.16 |